## Sheet1
ProjectID | ProjectName | CountyID | SourceOfFunds | FundingAmount | ImplementingAgency | Program | ConstituencyID | WardID | GPSCoordinates | ProjectType | ProjectLocation | ScopeOfWorks | IntakeCapacity_m3 | TreatmentCapacity_m3 | StorageCapacity_m3 | TreatedWaterMains_km | DistributionLines_km | NumberOfWaterKiosks | NumberOfConnections | WastewaterCapacity_m3 | TargetAreas | TargetBeneficiaries_Households | TargetBeneficiaries_Population | Contractor | Consultant | StartDate | PlannedEndDate | ActualEndDate | ProgressPercentage | TotalContractSum_KES | CumulativeExpenditure_KES | OutstandingCost_KES | ExchequerReleases_KES | SumOfPendingBills_KES | ApprovedBudgetFY2021_22 | ApprovedBudgetFY2021_23 | ApprovedBudgetFY2022_23 | ApprovedBudgetFY2022_24 | ApprovedBudgetFY2023_24 | ApprovedBudgetFY2023_25 | BudgetAllocationFY2024_25 | BudgetAllocationFY2024_26 | ImpactsOfTheProject | KeyChallenges | Remarks
5 | Water Supply Project | 1 | GoK | 5000000 | Water Board | Rural Water | 1 | 1 | -1.2921, 36.8219 | Water Supply | Nairobi | Install pipes and tanks | 1000 | 800 | 1200 | 10 | 15 | 5 | 200 | 500 | Urban slums | 1000 | 5000 | ABC Contractors | XYZ Consultants | 2023-01-01 | 2024-12-31 |  | 75 | 10000000 | 7500000 | 2500000 | 6000000 | 1500000 | 2000000 | 2500000 | 3000000 | 3500000 | 4000000 | 4500000 | 5000000 | 5500000 | Improved water access | Funding delays | On track
6 | Sewer Upgrade | 2 | AFD | 8000000 | Sanitation Dept | Urban Sanitation | 2 | 2 | -1.9432, 36.1234 | Sanitation | Mombasa | Upgrade sewer lines | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1500 | Coastal towns | 1500 | 7500 | DEF Builders | GHI Advisors | 2023-06-01 | 2025-06-30 |  | 50 | 12000000 | 6000000 | 6000000 | 5000000 | 2000000 | 3000000 | 3500000 | 4000000 | 4500000 | 5000000 | 5500000 | 6000000 | 6500000 | Better sanitation | Weather issues | Needs review